## functionallity
Functionallity
Homepage
Name | Assignee | MVP | Status | Start Date | Completion Data
General UI Functionality(Buttons/ Paths/ Control Logic) | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP#1 | Done | 2019-12-30 | 2020-02-03
Redirect to Store | Jinkai Fan, Mckenzie Busenius | MVP#1 | Done | 2020-01-29 | 2020-02-03
|  |  |  | 2019-12-30 to 2020-01-29 | 2020-02-03
Media Page
Name | Assignee | MVP | Status | Start Date | Completion Data
General UI Functionality(Buttons/ Paths/ Control Logic) | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP#1 | Done | 2019-11-25 | 2020-02-03
New banners (Sliding information, Maybe NHL scores etc) | andyofl1024@gmail.com, Mckenzie Busenius | MVP#1 | On hold
Play podcast within the app itself | andyofl1024@gmail.com, Mckenzie Busenius | MVP#1 | On hold
Play video within the app itself | Mckenzie Busenius, andyofl1024@gmail.com | MVP#1 | Working on it | 2019-11-25 | 2020-02-27
|  |  |  | 2019-11-25 | 2020-02-03 to 2020-02-27
User Account
Name | Assignee | MVP | Status | Start Date | Completion Data
General UI Functionality(Buttons/ Paths/ Control Logic) | Jinkai Fan | MVP#1 | Done | 2019-11-25 | 2020-03-25
User signup functionally | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP#2 | Done | 2020-01-01 | 2020-03-25
Protected Folder |  | MVP#2 | On hold
Private Folder |  | MVP#2 | On hold
New Video |  | MVP#2 | On hold
Search Videos within each folder |  | MVP#2 | On hold
Edit basic account information |  | MVP#2 | On hold
Logout option | Jinkai Fan | MVP#2 | Done | 2020-01-01 | 2020-03-25
Edit App settings |  | MVP#2 | On hold
|  |  |  | 2019-11-25 to 2020-01-01 | 2020-03-25
Contact Page
Name | Assignee | MVP | Status | Start Date | Completion Data
General UI Functionality(Buttons/ Paths/ Logic) | andyofl1024@gmail.com | MVP#1 | Done | 2019-11-25 | 2020-02-03
|  |  |  | 2019-11-25 | 2020-02-03