## serdachny-hockey
Serdachny Hockey
Project management includes design, documentation, user interface, AWS backend.
Project Presentation
Name | Owner | MVP | Status | Start Date | Due date | Completion(Late)
Title | Mckenzie Busenius | MVP #1 | Done | 2020-01-26 | 2020-01-31
Abstract | Mckenzie Busenius | MVP #1 | Done | 2020-01-26 | 2020-02-28
Project Poster | Mckenzie Busenius | MVP #1 | Done | 2020-02-29 | 2020-03-27
Live Presentation | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-03-30 | 2020-04-04 | 2020-04-09
|  |  |  | 2020-01-26 to 2020-03-30 | 2020-01-31 to 2020-04-04 | 2020-04-09
Documentation
Name | Owner | MVP | Status | Start Date | Due date | Completion(Late)
Requirements Doc | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2019-09-24 | 2020-03-17 | 2020-04-05
Code Quality Report | andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-03-30 | 2020-04-05 | 2020-04-05
Project Experience Report | andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-03-30 | 2020-04-05 | 2020-04-05
Testing Plan | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-01-29 | 2020-03-02 | 2020-04-05
Project Promotional Package | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-04-03 | 2020-04-05 | 2020-04-05
|  |  |  | 2019-09-24 to 2020-04-03 | 2020-03-02 to 2020-04-05 | 2020-04-05
Design
Name | Owner | MVP | Status | Start Date | Due date | Completion(Late)
Lo-Fi | Jinkai Fan, andyofl1024@gmail.com, Mckenzie Busenius | MVP #1 | Done | 2019-10-01 | 2019-10-11
Hi-Fi | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2019-10-15 | 2019-10-25
System Overview Diagram | Mckenzie Busenius | MVP #1 | Done | 2020-01-26 | 2020-03-17 | 2020-04-05
System UML's | Mckenzie Busenius, Jinkai Fan, andyofl1024@gmail.com | MVP #1 | Done | 2020-01-07 | 2020-03-09 | 2020-04-05
|  |  |  | 2019-10-01 to 2020-01-26 | 2019-10-11 to 2020-03-17 | 2020-04-05
User Interface
Name | Owner | MVP | Status | Start Date | Due date | Completion(Late)
Homepage | Jinkai Fan | MVP #1 | Done | 2019-11-05 | 2020-02-10
Media | andyofl1024@gmail.com | MVP #1 | Done | 2019-11-05 | 2020-02-10
UserAccounts | Jinkai Fan, andyofl1024@gmail.com | MVP #1 | Done | 2019-11-05 | 2020-02-10
ContactPage | andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2019-11-05 | 2020-02-10
|  |  |  | 2019-11-05 | 2020-02-10
AWS Backend
Name | Owner | MVP | Status | Start Date | Due date | Completion(Late)
Look into AWS Login Demo, Complete configurations for AWS for project | Mckenzie Busenius | MVP #1 | Done | 2019-12-27 | 2020-02-10
Configure member laptops | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-01-26 | 2020-02-24
Inform group members about stack | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | MVP #1 | Done | 2020-01-26 | 2020-02-24
Connect Xcode to AWS | Mckenzie Busenius | MVP #1 | Done | 2019-12-21 | 2020-01-05
MediaPage | Mckenzie Busenius | MVP #1 | Working on it | 2020-03-02 | 2020-03-17
HomePage | Mckenzie Busenius | MVP #1 | Working on it | 2020-03-02 | 2020-03-17
UserAccountPage | Mckenzie Busenius | MVP #2 | Working on it | 2020-03-02 | 2020-03-09
Contact Page | Mckenzie Busenius, Jinkai Fan | MVP #1 | Done | 2020-02-09 | 2020-02-24
|  |  |  | 2019-12-21 to 2020-03-02 | 2020-01-05 to 2020-03-17
Software Testing
Name | Owner | MVP | Status | Start Date | Due date | Completion(Late)
UI Testing MVP#1 | Jinkai Fan | MVP #1 | Working on it | 2020-03-30 | 2020-03-02 | 2020-04-05
UI Testing MVP#2 | Mckenzie Busenius | MVP #2 | Waiting for review |  | 2020-03-09
Functionality Testing#1 | andyofl1024@gmail.com | MVP #1 | Working on it | 2020-03-30 | 2020-03-02 | 2020-04-05
Functionality Testing#2 | Mckenzie Busenius | MVP #2 | Waiting for review |  | 2020-02-09
|  |  |  | 2020-03-30 | 2020-02-09 to 2020-03-09 | 2020-04-05