## project-wrap-up
Project Wrap-Up
Project Deliverables
Name | Owner | Status | Date | Late Completion
Program Requirements | Mckenzie Busenius | Done | 2020-04-05 | 2020-04-10
System Architecture | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | Done | 2020-04-05 | 2020-04-10
Role based access/ Security access | andyofl1024@gmail.com | Done | 2020-04-05 | 2020-04-10
Project Roadmap | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | Done | 2020-04-05 | 2020-04-10
Protoypes | Jinkai Fan, andyofl1024@gmail.com, Mckenzie Busenius | Done |  | 2020-04-10
Code Testing plan | Jinkai Fan | Done | 2020-04-05 | 2020-04-07
User Testing Plan | Jinkai Fan | Done | 2020-04-05 | 2020-04-07
Customer help/ User Help/ Knowledge base | Jinkai Fan | Stuck | 2020-04-05
Final Documentation Review | Mckenzie Busenius | Waiting for review | 2020-04-10 | 2020-04-10
Final Video Review | Jinkai Fan | Waiting for review | 2020-04-10 | 2020-04-10
Final Code Review | andyofl1024@gmail.com | Waiting for review | 2020-04-10 | 2020-04-10
|  |  | 2020-04-05 to 2020-04-10 | 2020-04-07 to 2020-04-10
Project Code/ Effective Summaries/ Presentations
Name | Owner | Status | Date | Late Completion
Power Point Representation | Mckenzie Busenius, andyofl1024@gmail.com, Jinkai Fan | Done | 2020-04-09
Project Requirements | Mckenzie Busenius, Jinkai Fan, andyofl1024@gmail.com | Done | 2020-04-09 | 2020-04-10
Project Experience Report | Jinkai Fan | Done | 2020-04-09
Code Quality Report | andyofl1024@gmail.com | Done | 2020-04-09
Project Promotional Package | Mckenzie Busenius | Done | 2020-04-09
Project Poster | Jinkai Fan | Done | 2020-04-09
Post Code to GitHub | Mckenzie Busenius | Done | 2020-04-09
Final Touches of UI | Mckenzie Busenius | Done | 2020-04-03
|  |  | 2020-04-03 to 2020-04-09 | 2020-04-10
Video Presentation
Name | Owner | Status | Date | Late Completion
Promotional Video | Jinkai Fan | Done | 2020-04-05
General Overview | Mckenzie Busenius | Done | 2020-04-05
HomePage | Jinkai Fan | Done | 2020-04-05
Media | andyofl1024@gmail.com | Done | 2020-04-05
Account | Mckenzie Busenius | Done | 2020-04-05
Contacts | andyofl1024@gmail.com | Done | 2020-04-05
Backend | Mckenzie Busenius | Done | 2020-04-05
Furutre Work/ Conculsion | andyofl1024@gmail.com | Done | 2020-04-05
2020-04-05